## FP
SUCCESSIVE PRINCIPLE: ROBUST BUDGETS & PLANS - that keeps! |  | Author: mail@compilot.dk | Rev. 2024-01-17a
| www.lichtenberg.org | compilot.dk
Disclaimer:
The use of this tool is under own risk and the Author can under no circumstances being held responsible for any errors in this tool neither misuse of this tool, what so ever.
Always use at least one other simple model or thumbs of rules to check the results.
The Successive Principle is one of the most powerful and efficient estimations methods in todays modern business and finance. The main principle is the three-point estimation which is easy to apprehend.
The method has proven itself through a numerous of projects with a high degree of accuracy predicting budgets and time plans! E.g. the Norwegian State has been using the method for many years and is mandatory.
Approx. 70% (2024) of Norwegian Highways, Tunnels and large IT Infra Structure projects conclude within budget!
ESTIMATION OF THE SOUROUNDINGS?
The challenge of the Successive Principle is the estimation of how much the surrounding poses uncertainty to the project. However, everyone knows that e.g. project management, portfolio management, variances in competencies, company maturity etc. can influence the project time and cost. So, why not estimate these as well ?
This is a very important part of the Successive Principle, as often 75-90% of all uncertainty is in the surroundings!
CASES
COMPILOT has used the method with success in a number of projects and business cases. E.g.:
● Development of a large HW/SW for Turbine Controller Platform, Client 1
● Development of a large HW/SW for Turbine Controller Platform, Client 2
● Development of a new 3 MW Direct Drive Wind Turbine
● Development of a new 6 MW Direct Drive Wind Turbine
● Financial Risk Assessment of a Large Offshore Wind Farm in UK, Vattenfall
● Financial Risk Assessment of a an Offshore Wind Farm in UK, German Client
The estimations provides:
● Overview of Top10 risk elements and basis for mitigation plans
● Robust plans, as the project could be frontloaded with resources
● Stimulated Team Spirit, as the engineering groups worked together
● Common insight in the project across departments
The Successive Principle - The Book.
Can be purchased via mail@compilot.dk
See further info on YouTube "Risk Management & EBIT Control".
E-Book can be purchased via Molio.dk
Uncertainty Share:
Surroundings
Uncertainty Share:
Tasks in the project
80%
20%
UNCERTAINTY SHARES:
THE MAIN THINGS THAT CAN GO WRONG
The Tool.
See futuraone.com

## Data
SUCCESSIVE PRINCIPLE: ROBUST BUDGETS & PLANS - That keeps | [15 empty] | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide | Hide
Rev. 2024-01-17a | [12 empty] | Author: COMPILOT.dk | [47 empty] | 1:100 | HandP125 |  |  |  | Index
[14 empty] | P % |  | GU | [44 empty] | 3 | 2.9 |  |  |  | 2
UNCERTAINTY ANALYSIS: |  |  | Construction - Scoping phase | [10 empty] | Limits | Code | [36 empty] | General Uncertainties | [8 empty] | 5 | 4.9 |  |  |  | 3
Identification of Risks & Opportunities | [13 empty] | 30% | xx,x% | [35 empty] | Costs: | -4 | [8 empty] | 5 | 4.65 |  |  |  | 4
|  |  |  | Analyse Uncertainty= | 12.72% | [8 empty] | 10% | xx,x% |  | 577 |  |  | 561 | [16 empty] | FINDING VALUES | [13 empty] | Income: | 124.5
[14 empty] | 2% | xx,x% |  |  | DeltaId: | 1e-07 |  |  |  | Tornado Diagram Data | [6 empty] | Tornado Diagram Data | [7 empty] | % estimated Min/ML/Max
Enter values/text in the light green cells. |  |  | 342.41 | 493.9603 | 645.5106 |  | 12.27% | 60.6201 | [8 empty] | Sorting out the Top Ten contributions to Uncertainty | [5 empty] | % estimated Min/ML/Max | [5 empty] | % Share |  | Un-sorted | [5 empty] | % Share |  | Sorted
[13 empty] | How can these influence, who long time the tasks are executed? | [6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  | Found | [5 empty] | Found | [8 empty] | https://www.youtube.com/watch?v=lVvQOdPr97E
Ref. | Incl. | General Uncertainties | Min | M.L. | Max |  | Mean | Std | Criticality | Var | P % |  | Notes | Skewness |  | SumInput | No. | Local No. | P % | Rank | P % | Min | M.L. | Max | Type | Text |  |  | Min | Mean | Max | P % | Check |  | Value |  | Min | Mean | Max |  | Text |  | P % | Min | Max | M.L. |  | Min | M.L. | Max |  | Co/In | Min | M.L. | Max | Mean | S(0) | S(%) | dTF+ | dTF-
A | 1 | Contracting strategy | -35 | 10 | 75 |  | 14 | 22 | 100% | 484 | 13.17% |  | Choice of contract form, etc. | 6.543% |  | 1 | 1 | 1 | 13.17% | 2 | 13.17% | 88.55% | 103.3% | 124.5% | 1.0327 | GU(A): Contracting strategy |  |  | 93.41% | 100% | 106.6% | 13.17% | 0% |  | 21.33% |  | 89.33% | 100% | 110.7% |  | #1: GU(C): Compet. & Experience level, P= 21,3% |  | 21.33% | 83.64% | 129.4% | 103.3% |  | 83.64% | 103.3% | 129.4% |  | 305.6706 | 88.55% | 103.3% | 124.5% | 104.6% | 7.197% | 157.1% | 4.58% | 0%
B | 1 | Interfaces | -25 | 0 | 50 |  | 5 | 15 | 100% | 225 | 6.123% |  | Legal, business and physical | 8.179% |  | 1 | 2 | 2 | 6.123% | 8 | 6.123% | 91.82% | 100% | 116.4% | 1.0327 | GU(B): Interfaces |  |  | 96.94% | 100% | 103.1% | 6.123% | 8.327e-15% |  | 13.17% |  | 93.41% | 100% | 106.6% |  | #2: GU(A): Contracting strategy, P= 13,2% |  | 13.17% | 88.55% | 124.5% | 103.3% |  | 88.55% | 103.3% | 124.5% |  | 305.6706 | 91.82% | 100% | 116.4% | 101.6% | 5 | 4.692% | 1.636% | 0%
C | 1 | Compet. & Experience level | -50 | 10 | 90 |  | 14 | 28 | 100% | 784 | 21.33% |  | For all partners involved. | 6.543% |  | 1 | 3 | 3 | 21.33% | 1 | 21.33% | 83.64% | 103.3% | 129.4% | 1.0327 | GU(C): Compet. & Experience level |  |  | 89.33% | 100% | 110.7% | 21.33% | 0% |  | 10.88% |  | 94.56% | 100% | 105.4% |  | #3: GU(H): Req. & quality control, P= 10,9% |  | 10.88% | 91.82% | 124.5% | 104.9% |  | 91.82% | 104.9% | 124.5% |  | 305.6706 | 83.64% | 103.3% | 129.4% | 104.6% | 14 | 13.14% | 4.58% | 0%
D | 1 | The Builders Org. | -5 | 10 | 17.5 |  | 8.5 | 4.5 | 100% | 20.25 | 0.5511% |  | Number of people and maturity. | -2.454% |  | 1 | 4 | 4 | 0.5511% | 19 | 0.5511% | 98.36% | 103.3% | 105.7% | 1.0327 | GU(D): The Builders Org. |  |  | 99.72% | 100% | 100.3% | 0.5511% | 3.036e-15% |  | 10.88% |  | 94.56% | 100% | 105.4% |  | #4: GU(F): External conditions, P= 10,9% |  | 10.88% | 91.82% | 124.5% | 103.3% |  | 91.82% | 103.3% | 124.5% |  | 305.6706 | 98.36% | 103.3% | 105.7% | 102.8% | 8.5 | 7.976% | 2.781% | 0%
E | 1 | Project Org. | -15 | -5 | 10 |  | -4 | 5 | 100% | 25 | 0.6803% |  | For alle involved partners. | 0% |  | 1 | 5 | 5 | 0.6804% | 18 | 0.6803% | 100% | 100% | 100% | 1.0327 | GU(E): Project Org. |  |  | 99.66% | 100% | 100.3% | 0.6803% | 2.168e-15% |  | 8.817% |  | 95.59% | 100% | 104.4% |  | #5: Opg15: Accommodation, P= 8,8% |  | 8.817% | 20.41% | 204.1% | 91.84% |  | 20.41% | 91.84% | 204.1% |  | 0 | 100% | 100% | 100% | 100% | -4 | -3.753% | 0% | 0%
F | 1 | External conditions | -25 | 10 | 75 |  | 16 | 20 | 100% | 400 | 10.88% |  | The physical environment /surroundings | 9.814% |  | 1 | 6 | 6 | 10.89% | 4 | 10.88% | 91.82% | 103.3% | 124.5% | 1.0327 | GU(F): External conditions |  |  | 94.56% | 100% | 105.4% | 10.88% | 0% |  | 6.123% |  | 96.94% | 100% | 103.1% |  | #6: Opg13: Raw house, P= 6,1% |  | 6.123% | 71.43% | 142.9% | 95.24% |  | 71.43% | 95.24% | 142.9% |  | 305.6706 | 91.82% | 103.3% | 124.5% | 105.2% | 16 | 15.01% | 5.234% | 0%
G | 1 | Construction market index | -10 | 5 | 25 |  | 6 | 7 | 100% | 49 | 1.333% |  | Boom | 1.636% |  | 1 | 7 | 7 | 1.333% | 12 | 1.333% | 96.73% | 101.6% | 108.2% | 1.0327 | GU(G): Construction market index |  |  | 99.33% | 100% | 100.7% | 1.333% | -7.806e-15% |  | 6.123% |  | 96.94% | 100% | 103.1% |  | #7: GU(I): Political issues, P= 6,1% |  | 6.123% | 91.82% | 116.4% | 103.3% |  | 91.82% | 103.3% | 116.4% |  | 305.6706 | 96.73% | 101.6% | 108.2% | 102% | 6 | 5.63% | 1.963% | 0%
H | 1 | Req. & quality control | -25 | 15 | 75 |  | 19 | 20 | 100% | 400 | 10.88% |  | Throughout the project. | 6.543% |  | 1 | 8 | 8 | 10.89% | 3 | 10.88% | 91.82% | 104.9% | 124.5% | 1.0327 | GU(H): Req. & quality control |  |  | 94.56% | 100% | 105.4% | 10.88% | 0% |  | 6.123% |  | 96.94% | 100% | 103.1% |  | #8: GU(B): Interfaces, P= 6,1% |  | 6.123% | 91.82% | 116.4% | 100% |  | 91.82% | 100% | 116.4% |  | 305.6706 | 91.82% | 104.9% | 124.5% | 106.2% | 19 | 17.83% | 6.216% | 0%
I | 1 | Political issues | -25 | 10 | 50 |  | 11 | 15 | 100% | 225 | 6.123% |  | The decision-makers, supporters and opponents. Political agenda. | 1.636% |  | 1 | 9 | 9 | 6.123% | 7 | 6.123% | 91.82% | 103.3% | 116.4% | 1.0327 | GU(I): Political issues |  |  | 96.94% | 100% | 103.1% | 6.123% | 8.327e-15% |  | 3.293% |  | 98.35% | 100% | 101.6% |  | #9: Opg40: Other, P= 3,3% |  | 3.293% | 43.48% | 163% | 97.83% |  | 43.48% | 97.83% | 163% |  | 305.6706 | 91.82% | 103.3% | 116.4% | 103.6% | 11 | 10.32% | 3.599% | 0%
J | 1 | Geographic index | 5 | 15 | 35 |  | 17 | 6 | 100% | 36 | 0.9796% |  | Where to build | 3.271% |  | 1 | 10 | 10 | 0.9797% | 15 | 0.9796% | 101.6% | 104.9% | 111.5% | 1.0327 | GU(J): Geographic index |  |  | 99.51% | 100% | 100.5% | 0.9796% | -9.368e-15% |  | 3.293% |  | 98.35% | 100% | 101.6% |  | #10: Opg16: Installations, P= 3,3% |  | 3.293% | 50% | 187.5% | 87.5% |  | 50% | 87.5% | 187.5% |  | 305.6706 | 101.6% | 104.9% | 111.5% | 105.6% | 17 | 15.95% | 5.562% | 0%
K | 1 | Media | -5 | 0 | 25 |  | 4 | 6 | 100% | 36 | 0.9796% |  | TV, FB, LinkedIn, X, radio | 6.543% |  | 1 | 11 | 11 | 0.9798% | 14 | 0.9796% | 98.36% | 100% | 108.2% | 1.0327 | GU(K): Media |  |  | 99.51% | 100% | 100.5% | 0.9796% | -9.368e-15% |  | 2.721% |  | 98.64% | 100% | 101.4% |  | #11: GU(Z): Analysis quality, P= 2,7% |  | 2.721% | 95.09% | 111.5% | 103.3% |  | 95.09% | 103.3% | 111.5% |  | 305.6706 | 98.36% | 100% | 108.2% | 101.3% | 4 | 3.753% | 1.309% | 0%
Z | 1 | Analysis quality | -15 | 10 | 35 |  | 10 | 10 | 100% | 100 | 2.721% |  | Description of the tasks, composition of the analysis group, number of participants, facilitator experiences and other aspects | 0% |  | 1 | 12 | 12 | 2.721% | 11 | 2.721% | 95.09% | 103.3% | 111.5% | 1.0327 | GU(Z): Analysis quality |  |  | 98.64% | 100% | 101.4% | 2.721% | 8.674e-15% |  | 1.333% |  | 99.33% | 100% | 100.7% |  | #12: GU(G): Construction market index, P= 1,3% |  | 1.333% | 96.73% | 108.2% | 101.6% |  | 96.73% | 101.6% | 108.2% |  | 305.6706 | 95.09% | 103.3% | 111.5% | 103.3% | 10 | 9.383% | 3.271% | 0%
|  |  | General Uncertainties : |  |  |  | 120.5 | 132.3% |  | 2784.25 | 75.77% | [45 empty] | 106.572 | 257.1% | 140.7% | 100%
[5 empty] | Analyse Uncertainty= |  | 12.72% |  |  | Check | 100% |  | CONTACT COMPILOT.dk for free support. | [39 empty] | Tasks
|  |  | Unit - Tasks | Min. | [47 empty] | Costs: | 0 | 0%
Ref. | Incl. | Tasks | Min | M.L. | Max |  | Mean | Std | Criticality | Var | P % |  | Notes. | Skewness | [37 empty] | Income: | 305.6706 | 100%
11 | 1 | Demolition | 5 | 10 | 35 | 70.42% | 14 | 6 | 100% | 36 | 0.9796% |  | This is a simple model, which shows the principles of the method. | 200% |  | 1 | 13 | 1 | 0.9798% | 13 | 0.9796% | 35.71% | 71.43% | 250% | 1.0327 | Opg11: Demolition |  |  | 99.51% | 100% | 100.5% | 0.9796% | -9.368e-15% |  | 0.9796% | [5 empty] | #13: Opg11: Demolition |  |  | 35.71% | 250% | 71.43% | [6 empty] | 305.6706
12 | 1 | Building site | 25 | 30 | 50 |  | 33 | 5 | 100% | 25 | 0.6803% |  |  | 50% |  | 1 | 14 | 2 | 0.6804% | 17 | 0.6803% | 75.76% | 90.91% | 151.5% | 1.0327 | Opg12: Building site |  |  | 99.66% | 100% | 100.3% | 0.6803% | 2.168e-15% |  | 0.9796% | [5 empty] | #14: GU(K): Media |  |  | 98.36% | 108.2% | 100%
13 | 1 | Raw house | 75 | 100 | 150 |  | 105 | 15 | 100% | 225 | 6.123% |  | New principles need to be designed. | 25% |  | 1 | 15 | 3 | 6.123% | 6 | 6.123% | 71.43% | 95.24% | 142.9% | 1.0327 | Opg13: Raw house |  |  | 96.94% | 100% | 103.1% | 6.123% | 8.327e-15% |  | 0.9796% | [5 empty] | #15: GU(J): Geographic index |  |  | 101.6% | 111.5% | 104.9%
14 | 1 | Closing facades | 6 | 10 | 15 |  | 10.2 | 1.8 | 100% | 3.24 | 0.08817% |  |  | 10% |  | 1 | 16 | 4 | 0.08833% | 20 | 0.08817% | 58.82% | 98.04% | 147.1% | 1.0327 | Opg14: Closing facades |  |  | 99.96% | 100% | 100% | 0.08817% | 7.145e-15% |  | 0.6803% | [5 empty] | #16: Opg31: Land purchase |  |  | 55.56% | 194.4% | 83.33%
15 | 1 | Accommodation | 10 | 45 | 100 |  | 49 | 18 | 100% | 324 | 8.817% |  | The décor is not in place. | 44.44% |  | 1 | 17 | 5 | 8.817% | 5 | 8.817% | 20.41% | 91.84% | 204.1% | 1.0327 | Opg15: Accommodation |  |  | 95.59% | 100% | 104.4% | 8.817% | 0% |  | 0.6803% | [5 empty] | #17: Opg12: Building site |  |  | 75.76% | 151.5% | 90.91%
16 | 1 | Installations | 20 | 35 | 75 |  | 40 | 11 | 100% | 121 | 3.293% |  |  | 71.43% |  | 2 | 19 | 7 | 3.293% | 10 | 3.293% | 50% | 87.5% | 187.5% | 1.0327 | Opg16: Installations |  |  | 98.35% | 100% | 101.6% | 3.293% | 6.939e-15% |  | 0.5511% | [5 empty] | #19: GU(D): The Builders Org. |  |  | 98.36% | 105.7% | 103.3%
17 | 1 | Landscape | 8 | 12 | 15 |  | 11.8 | 1.4 | 100% | 1.96 | 0.05334% |  |  | -8.333% |  | 1 | 20 | 8 | 0.05354% | 23 | 0.05334% | 67.8% | 101.7% | 127.1% | 1.0327 | Opg17: Landscape |  |  | 99.97% | 100% | 100% | 0.05334% | -4.304e-15% |  | 0.08817% | [5 empty] | #20: Opg14: Closing facades |  |  | 58.82% | 147.1% | 98.04%
21 | 1 | Projecting | 10.52 | 13.15 | 16.4375 | 6.07% | 13.2815 | 1.1835 | 100% | 1.4007 | 0.03812% |  | One % rate of contracts (mean). | 5% |  | 1 | 21 | 9 | 0.03833% | 25 | 0.03812% | 79.21% | 99.01% | 123.8% | 1.0327 | Opg21: Projecting |  |  | 99.98% | 100% | 100% | 0.03812% | -3.578e-16% |  | 0.05532% | [5 empty] | #21: Opg38: Financing |  |  | 58.82% | 147.1% | 98.04%
22 | 1 | Counselling | 3.945 | 6.575 | 9.8625 |  | 6.7065 | 1.1835 | 100% | 1.4007 | 0.03812% |  | One % rate of contracts (mean). | 10% |  | 1 | 22 | 10 | 0.03834% | 24 | 0.03812% | 58.82% | 98.04% | 147.1% | 1.0327 | Opg22: Counselling |  |  | 99.98% | 100% | 100% | 0.03812% | -3.74e-16% |  | 0.05334% | [5 empty] | #22: Opg33: Internal roads |  |  | 20.83% | 166.7% | 104.2%
23 | 1 | Construction management | 0.789 | 1.315 | 1.9725 |  | 1.3413 | 0.2367 | 100% | 0.056027 | 0.001525% |  | One % rate of contracts (mean). | 10% |  | 1 | 23 | 11 | 0.001755% | 31 | 0.001525% | 58.82% | 98.04% | 147.1% | 1.0327 | Opg23: Construction management |  |  | 100% | 100% | 100% | 0.001525% | 6.646e-15% |  | 0.05334% | [5 empty] | #23: Opg17: Landscape |  |  | 67.8% | 127.1% | 101.7%
24 | 1 | Supervision | 0.789 | 1.315 | 1.9725 |  | 1.3413 | 0.2367 | 100% | 0.056027 | 0.001525% |  | One % rate of contracts (mean). | 10% |  | 1 | 24 | 12 | 0.001765% | 30 | 0.001525% | 58.82% | 98.04% | 147.1% | 1.0327 | Opg24: Supervision |  |  | 100% | 100% | 100% | 0.001525% | 6.646e-15% |  | 0.03812% | [5 empty] | #24: Opg22: Counselling |  |  | 58.82% | 147.1% | 98.04%
31 | 1 | Land purchase | 10 | 15 | 35 | 10.51% | 18 | 5 | 100% | 25 | 0.6803% |  |  | 100% |  | 1 | 25 | 13 | 0.6806% | 16 | 0.6803% | 55.56% | 83.33% | 194.4% | 1.0327 | Opg31: Land purchase |  |  | 99.66% | 100% | 100.3% | 0.6803% | 2.168e-15% |  | 0.03812% | [5 empty] | #25: Opg21: Projecting |  |  | 79.21% | 123.8% | 99.01%
32 | 1 | Geotechnical investigation | 1 | 2 | 3 |  | 2 | 0.4 | 100% | 0.16 | 0.004354% |  |  | 0% |  | 1 | 26 | 14 | 0.004614% | 28 | 0.004354% | 50% | 100% | 150% | 1.0327 | Opg32: Geotechnical investigation |  |  | 100% | 100% | 100% | 0.004354% | -8.283e-15% |  | 0.02119% | [5 empty] | #26: Opg97: Unk Unks Group 1 |  |  | 12.81% | 187.2% | 100%
33 | 1 | Internal roads | 1 | 5 | 8 |  | 4.8 | 1.4 | 100% | 1.96 | 0.05334% |  |  | -20% |  | 1 | 27 | 15 | 0.05361% | 22 | 0.05334% | 20.83% | 104.2% | 166.7% | 1.0327 | Opg33: Internal roads |  |  | 99.97% | 100% | 100% | 0.05334% | -4.304e-15% |  | 0.009796% | [5 empty] | #27: Opg34: Terrain regulation |  |  | 45.45% | 181.8% | 90.91%
34 | 1 | Terrain regulation | 1 | 2 | 4 |  | 2.2 | 0.6 | 100% | 0.36 | 0.009796% |  |  | 50% |  | 1 | 28 | 16 | 0.01008% | 27 | 0.009796% | 45.45% | 90.91% | 181.8% | 1.0327 | Opg34: Terrain regulation |  |  | 100% | 100% | 100% | 0.009796% | 7.955e-16% |  | 0.004354% | [5 empty] | #28: Opg32: Geotechnical investigation |  |  | 50% | 150% | 100%
35 | 1 | Securing the outer rim | 1.5 | 2 | 3 |  | 2.1 | 0.3 | 100% | 0.09 | 0.002449% |  |  | 25% |  | 1 | 29 | 17 | 0.002739% | 29 | 0.002449% | 71.43% | 95.24% | 142.9% | 1.0327 | Opg35: Securing the outer rim |  |  | 100% | 100% | 100% | 0.002449% | 2.974e-15% |  | 0.002449% | [5 empty] | #29: Opg35: Securing the outer rim |  |  | 71.43% | 142.9% | 95.24%
36 | 1 | Building permit | 0.9 | 1 | 1.5 |  | 1.08 | 0.12 | 100% | 0.0144 | 0.0003919% |  |  | 40% |  | 1 | 30 | 18 | 0.0006919% | 33 | 0.0003919% | 83.33% | 92.59% | 138.9% | 1.0327 | Opg36: Building permit |  |  | 100% | 100% | 100% | 0.0003919% | 8.914e-15% |  | 0.001525% | [5 empty] | #30: Opg24: Supervision |  |  | 58.82% | 147.1% | 98.04%
37 | 1 | Insurances | 0.5 | 1 | 1.5 |  | 1 | 0.2 | 100% | 0.04 | 0.001088% |  |  | 0% |  | 1 | 31 | 19 | 0.001398% | 32 | 0.001088% | 50% | 100% | 150% | 1.0327 | Opg37: Insurances |  |  | 100% | 100% | 100% | 0.001088% | 6.256e-15% |  | 0.001525% | [5 empty] | #31: Opg23: Construction management |  |  | 58.82% | 147.1% | 98.04%
38 | 1 | Financing | 4.7528 | 7.9213 | 11.8819 |  | 8.0797 | 1.4258 | 100% | 2.033 | 0.05532% |  | One % rate of all costs (mean). | 10% |  | 1 | 32 | 20 | 0.05564% | 21 | 0.05532% | 58.82% | 98.04% | 147.1% | 1.0327 | Opg38: Financing |  |  | 99.97% | 100% | 100% | 0.05532% | 1.16e-15% |  | 0.001088% | [5 empty] | #32: Opg37: Insurances |  |  | 50% | 150% | 100%
40 | 1 | Other | 20 | 45 | 75 | 12.32% | 46 | 11 | 100% | 121 | 3.293% |  | Everything else | 11.11% |  | 1 | 33 | 21 | 3.293% | 9 | 3.293% | 43.48% | 97.83% | 163% | 1.0327 | Opg40: Other |  |  | 98.35% | 100% | 101.6% | 3.293% | 6.939e-15% |  | 0.0003919% | [5 empty] | #33: Opg36: Building permit |  |  | 83.33% | 138.9% | 92.59%
[7 empty] | Mean | Std | S(T) | Var
97 | 1 | Number of Unknowns UnKnowns: Tasks | 1 | 2 | 4 |  | 2.2 | 0.6 | 27.27% | 0.4761 |  |  | Think of a previous project. How many Unknown Unknowns task came later?
| 1 | Value per Unknowns Unknown | 0.75 | 1 | 2 |  | 1.15 | 0.25 | 21.74% | 0.3025 |  |  | Think of a previous project. How many hours per task?
97 | 1 | Unk Unks Group 1 | 0.32404 | 2.53 | 4.736 |  | 2.53 | 0.88238 | 100% | 0.7786 | 0.02119% |  | Min, M.L. and Max values includes TF. | -1.755e-14% |  | 1 | 34 | 22 | 0.02153% | 26 | 0.02119% | 12.81% | 100% | 187.2% | 1.0327 | Opg97: Unk Unks Group 1 |  |  | 99.99% | 100% | 100% | 0.02119% | 4.096e-15% |  | #N/A | [5 empty] | #N/A
|  | Relative values | 12.81% | 100% | 187.2%
[10 empty] | 890.5494 | 24.23% |  | Sum of tasks
[7 empty] | 373.4603 | Total Mean excl. GU's
MAIN RESULTS
|  |  | Min | Mean | Max |  | S(%) | Std | Var
|  | Positive side | #REF! | #REF! | #REF! |  | 0% | #REF! | #REF! |  | 0%
|  |  | Min | Mean | Max |  | S(%) | Std | Var
|  | Negative side | #REF! | #REF! | #REF! |  | 0% | #REF! | #REF! |  | 0%
#REF!
The budget is with 95% probability between 75 to 125 % of the Mean values.
|  |  | Min | Mean | Max |  | Std |  | Std | Var
Main result: |  |  | 342.41 | 493.9603 | 645.5106 |  | 12.27% |  | 60.6201 | 3674.7994
|  |  | Mean - 2,5*S |  | Mean + 2,5*S | [5 empty] | Include GU: | 0 | 1: Include, 0: Show OF's
|  |  | 69.32% | 100% | 130.7% | of Mean
|  |  |  | Better | Worse
Assumed BUDGET: |  |  | 85% | 85% | 15% |  | 556.789 | Min. | 1.0364 | Budget = Mean +1,04 * Std.
|  |  |  | 112.7% | Budget factor
The Assumed budget is considered as: |  |  | Robust
Extra Budget set in the P-Curve: |  |  | 95% |  |  |  |  | Uncertainty in the analyse U(P(xx))= | 12.72% | (P85-P50)/P50
TASK BUDGET
[18 empty] | DeltaId: | -1e-05
|  | Here alle element contributing are listed: | [16 empty] | no*Delta | 2: Original
|  |  |  | Assumed | ETC % |  | ETC | [12 empty] | 1: 1; 2: 2; 3: 3; % estimated Min/ML/Max 4: 4; % estimated Min/ML/Max 5: 5; % estimated Min/ML/Max 6: 6; % estimated Min/ML/Max 7: 7
|  | Tasks & General Uncertainties | Mean | Budget | ETC % |  | Budget | [9 empty] | No. | Local No. | Value | 1: Rank; 2: Value; % estimated Min/ML/Max 6: Type; % estimated Min/ML/Max 7: Text | [10 empty] | Value |  | Text
| Tasks | Demolition | 14 | 15.7807 | 100% |  | 15.7807 | Opg. | [7 empty] | 1 | 1 | 9 | 15.7807 | 1: 10; 2: 15.7807; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.9: Demolition | [10 empty] | 118.3554 |  | #1: Opg.7: Raw house
|  | Building site | 33 | 37.1974 | 100% |  | 37.1974 | Opg. | [7 empty] | 1 | 2 | 8 | 37.1974 | 1: 5; 2: 37.1974; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.8: Building site | [10 empty] | 55.2325 |  | #2: Opg.5: Accommodation
|  | Raw house | 105 | 118.3554 | 100% |  | 118.3554 | Opg. | [7 empty] | 1 | 3 | 7 | 118.3553 | 1: 1; 2: 118.3554; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.7: Raw house | [10 empty] | 51.8509 |  | #3: Opg.12: Other
|  | Closing facades | 10.2 | 11.4974 | 100% |  | 11.4974 | Opg. | [7 empty] | 1 | 4 | 6 | 11.4973 | 1: 16; 2: 11.4974; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.6: Closing facades | [10 empty] | 45.0878 |  | #4: Opg.4: Installations
|  | Accommodation | 49 | 55.2325 | 100% |  | 55.2325 | Opg. | [7 empty] | 1 | 5 | 5 | 55.2324 | 1: 2; 2: 55.2325; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.5: Accommodation | [10 empty] | 37.1974 |  | #5: Opg.8: Building site
|  | Installations | 40 | 45.0878 | 100% |  | 45.0878 | Opg. | [7 empty] | 1 | 6 | 4 | 45.0877 | 1: 4; 2: 45.0878; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.4: Installations | [10 empty] | 21.4167 |  | #6: G.U.4: Req. & quality control
|  | Landscape | 11.8 | 13.3009 | 100% |  | 13.3009 | Opg. | [7 empty] | 1 | 7 | 3 | 13.3008 | 1: 14; 2: 13.3009; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.3: Landscape | [10 empty] | 20.2895 |  | #7: Opg.4: Land purchase
|  | Projecting | 13.2815 | 14.9708 | 100% |  | 14.9708 | Opg. | [7 empty] | 1 | 8 | 2 | 14.9707 | 1: 13; 2: 14.9708; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.2: Projecting | [10 empty] | 19.1623 |  | #8: G.U.2: Geographic index
|  | Counselling | 6.7065 | 7.5595 | 100% |  | 7.5595 | Opg. | [7 empty] | 1 | 9 | 1 | 7.5594 | 1: 19; 2: 7.5595; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.1: Counselling | [10 empty] | 18.0351 |  | #9: G.U.6: External conditions
|  | Construction management | 1.3413 | 1.5119 | 100% |  | 1.5119 | Opg. |  |  | Analysis Group | 1:100 |  |  |  | 1 | 10 | 2 | 1.5118 | 1: 28; 2: 1.5119; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.2: Construction management | [10 empty] | 15.7807 |  | #10: Opg.9: Demolition
|  | Supervision | 1.3413 | 1.5119 | 100% |  | 1.5119 | Opg. |  |  | Factor A | 3 |  |  |  | 1 | 11 | 3 | 1.5118 | 1: 29; 2: 1.5119; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.3: Supervision | [10 empty] | 15.7807 |  | #11: G.U.11: Contracting strategy
|  | Land purchase | 18 | 20.2895 | 100% |  | 20.2895 | Opg. |  |  | Divisor A | 5 |  |  |  | 1 | 12 | 4 | 20.2894 | 1: 7; 2: 20.2895; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.4: Land purchase | [10 empty] | 15.7807 |  | #12: G.U.9: Compet. & Experience level
|  | Geotechnical investigation | 2 | 2.2544 | 100% |  | 2.2544 | Opg. |  |  | Divisor B | 5 |  |  |  | 1 | 13 | 5 | 2.2543 | 1: 27; 2: 2.2544; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.5: Geotechnical investigation | [10 empty] | 14.9708 |  | #13: Opg.2: Projecting
|  | Internal roads | 4.8 | 5.4105 | 100% |  | 5.4105 | Opg. | [7 empty] | 1 | 14 | 6 | 5.4104 | 1: 22; 2: 5.4105; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.6: Internal roads | [10 empty] | 13.3009 |  | #14: Opg.3: Landscape
|  | Terrain regulation | 2.2 | 2.4798 | 100% |  | 2.4798 | Opg. | [7 empty] | 1 | 15 | 7 | 2.4797 | 1: 25; 2: 2.4798; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.7: Terrain regulation | [10 empty] | 12.3991 |  | #15: G.U.3: Political issues
|  | Securing the outer rim | 2.1 | 2.3671 | 100% |  | 2.3671 | Opg. | [7 empty] | 1 | 16 | 8 | 2.3669 | 1: 26; 2: 2.3671; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.8: Securing the outer rim | [10 empty] | 11.4974 |  | #16: Opg.6: Closing facades
|  | Building permit | 1.08 | 1.2174 | 100% |  | 1.2174 | Opg. | [7 empty] | 1 | 17 | 9 | 1.2172 | 1: 30; 2: 1.2174; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.9: Building permit | [10 empty] | 9.5811 |  | #17: G.U.8: The Builders Org.
|  | Insurances | 1 | 1.1272 | 100% |  | 1.1272 | Opg. | [7 empty] | 1 | 18 | 10 | 1.127 | 1: 31; 2: 1.1272; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.10: Insurances | [10 empty] | 9.1074 |  | #18: Opg.11: Financing
|  | Financing | 8.0797 | 9.1074 | 100% |  | 9.1074 | Opg. | [7 empty] | 1 | 19 | 11 | 9.1072 | 1: 18; 2: 9.1074; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.11: Financing | [10 empty] | 7.5595 |  | #19: Opg.1: Counselling
|  | Other | 46 | 51.8509 | 100% |  | 51.8509 | Opg. | [7 empty] | 1 | 20 | 12 | 51.8507 | 1: 3; 2: 51.8509; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.12: Other | [10 empty] | 6.7632 |  | #20: G.U.5: Construction market index
|  | Unk Unks Group 1 | 2.53 | 2.8518 | 100% |  | 2.8518 | Opg. | [7 empty] | 1 | 21 | 13 | 2.8516 | 1: 24; 2: 2.8518; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: Opg.13: Unk Unks Group 1 | [10 empty] | 5.636 |  | #21: G.U.10: Interfaces
| General Uncertainties | Contracting strategy | 14 | 15.7807 | 100% |  | 15.7807 | G.U. | [7 empty] | 1 | 22 | 11 | 15.7805 | 1: 11; 2: 15.7807; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.11: Contracting strategy
|  | Interfaces | 5 | 5.636 | 100% |  | 5.636 | G.U. | [7 empty] | 1 | 23 | 10 | 5.6357 | 1: 21; 2: 5.636; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.10: Interfaces
|  | Compet. & Experience level | 14 | 15.7807 | 100% |  | 15.7807 | G.U. | [7 empty] | 1 | 24 | 9 | 15.7805 | 1: 12; 2: 15.7807; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.9: Compet. & Experience level
|  | The Builders Org. | 8.5 | 9.5811 | 100% |  | 9.5811 | G.U. | [7 empty] | 1 | 25 | 8 | 9.5809 | 1: 17; 2: 9.5811; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.8: The Builders Org.
|  | Project Org. | -4 | -4.5088 | 100% |  | -4.5088 | G.U. | [7 empty] | 1 | 26 | 7 | -4.509 | 1: 32; 2: -4.5088; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.7: Project Org.
|  | External conditions | 16 | 18.0351 | 100% |  | 18.0351 | G.U. | [7 empty] | 1 | 27 | 6 | 18.0348 | 1: 9; 2: 18.0351; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.6: External conditions
|  | Construction market index | 6 | 6.7632 | 100% |  | 6.7632 | G.U. | [7 empty] | 1 | 28 | 5 | 6.7629 | 1: 20; 2: 6.7632; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.5: Construction market index
|  | Req. & quality control | 19 | 21.4167 | 100% |  | 21.4167 | G.U. | [7 empty] | 1 | 29 | 4 | 21.4164 | 1: 6; 2: 21.4167; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.4: Req. & quality control
|  | Political issues | 11 | 12.3991 | 100% |  | 12.3991 | G.U. | [7 empty] | 1 | 30 | 3 | 12.3988 | 1: 15; 2: 12.3991; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.3: Political issues
|  | Geographic index | 17 | 19.1623 | 100% |  | 19.1623 | G.U. | [7 empty] | 1 | 31 | 2 | 19.162 | 1: 8; 2: 19.1623; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.2: Geographic index
|  | Media | 4 | 4.5088 | 100% |  | 4.5088 | G.U. | [7 empty] | 1 | 32 | 1 | 4.5085 | 1: 23; 2: 4.5088; % estimated Min/ML/Max 6: 1.0327; % estimated Min/ML/Max 7: G.U.1: Media
|  | Total | 483.9603 | 545.5171 |  |  | 545.5171
Mean: The target for the project group
Budget: The allocated budget, front loading the budget
Notes: (Choosing No. Std. = 2.5)
That is: With 1% probability the tasks can be finished with less than 'Min' and with 98,8% probability they will not exceed 'Max'.
One can choose a robust budget figure, by using Mean + 1* Standard deviation, which leads to approx. 82% probability. See diagram sheet.
|  | Abbreviations: |  | C.I.: Confidence Interval
M.L.: Most Likely
P: Priority = the variance
P %: The Percentage P contributes to the total uncertainty
For PlotData
|  |  |  | 2 | 2.275% |  | 97.72% | 95.45% |  | Negative | Save | Not actual
[10 empty] | Positive | Consume
|  |  |  | The budget is with 95% probability between 75 to 125 % of the Mean values. | 75.46% |  | 124.5%
|  |  | P(GU's): | 75.77% |  | P(85) |  | P(85) | P(85) Budget
|  |  | P(Tasks): | 24.23% |  | P(95) |  |  | P(95) Budget
[6 empty] | P(50) |  |  | P(50) Budget
|  |  | Analyse Uncertainty= | 12.72%
|  |  | Diagram text box: | P(GU's): 75,8% P(Tasks): 24,2%
|  |  | Project name: | Construction - Scoping phase
|  |  | Diagram text box: | early-quality-assuring-construction-project_2024-11-19a.xlsx
|  |  | Diagram text box: | RESULT: Min= 342 Mean= 494 Max= 646 Min. & GU's = 120,5
|  |  |  | 342.41 |  | 493.9603 |  | 645.5106
|  |  |  | 0 |  | 0 |  | 0
|  |  |  | #.### |  | #.### |  | #.###
|  |  |  | Min= 342 |  | Mean= 494 |  | Max= 646
Analyse Uncertainty= 13 %
Note:
+/- 1,0 * Std equals 68,3 % C.I.
+/- 1,44* Std equals 85,0 % C.I.
+/- 2,0 * Std equals 95,5 % C.I.
+/- 2,5 * Std equals 98,8 % C.I.
+/- 3,0 * Std equals 99,7 % C.I.
Note:
Choose de coloured P% elementer and decompose them into 2-4 sub elements.
Make hereafter nye estimations - only of these.
Basic formulas (Task 'in'):
Mean[in] = (Min[i] + 3*M.L.[i] + Max[i])/5
Std[i] = (Max[i] - Min[i])/5; Var[i] = Stdv[i] * Stdv[i]
Prio[i] = Var[i]/∑(Var[i]); P[i]% = Prio[i]*100/∑(P[i])
Main assumption for calculations:
It is assumed that the tasks and general Uncertainties are mutually independent and each other.
In some cases this can not be satisfied. Hence you have to add some extra variance, e.g. adding an extra overall factor, despite it can be difficult to estimate the influence on the results.
EFFECTIVE PROGRAM: FUTURA
The program has been developed for more than 20 years and supports the entire Successive Process, ensuring an effective estimation process and subsequent reporting from the analyses. The program is used for estimating tunnel and highway projects and other large complex projects in the public sector and the private sector.
HKS-Consult is a distributor of FUTURA. Call on M +45 2629 8240 and get a free demonstration of the program. For example, on one of your projects.
Disclaimer:
The use of this toll is under own risk and the Author can under no circumstances being held responsible for any errors in this tool neither misuse of this tool, what so ever.
Always use at least one other simple model or thumbs of rules to check the results.
Note on BH2: Henrik K Søndergaard: Found in the Steen's handbook p125. Also used in the Futura program.
Note on BK2: Henrik K Søndergaard: Found in the Steen's handbook p125. Also used in the Futura program.
Note on J10: HKS Consult: To be used after some training in the method. IF an element is not critical at all then Criticality=0% and the uncertainty is set = 0 but the Mean value still be added to the total Mean IF an element if fully contributing to uncertainty the set value = 100%
Note on K10: HKS Consult: Variance = Std^2
Note on T10: HKS Consult: To make RANK work an small 1E-6 factor to No. Is added. This make Rank work, even if there is more than 1 with value 0(zero)
Note on I23: Henrik K Søndergaard: The Transformation Factor
Note on K48: HKS-Consult: Note special approach for Numbers * Costs
Note on J59: Henrik K Søndergaard: Include =0, as a Post can contribute even in the Mean=0
Note on J63: Henrik K Søndergaard: Include =0, as a Post can contribute even in the Mean=0
Note on T83: HKS Consult: To make RANK work an small 1E-6 factor to No. Is added. This make Rank work, even if there is more than 1 with value 0(zero)

## Plot (hidden)
PLOT OF 3PE DATA |  | Plot data
<> | [15 empty] | For controlling plot sequence
Tasks |  | 4 | 1 | 3 | 2 | [10 empty] | 4 | Plot of Min, M.L. Max and Mean
RefNo. | TF | Mean | Min | M.L. | Max |  | x1 | x2 | y1 | y2 |  | x2 | x3 | y2 | y3 | No. | Serie No. |  | Plot
11 | 100% | 14 | 5 | 10 | 35 | 11.a | 14 | 14 | 5 | 10 | 11.b | 14 | 14 | 10 | 35 | 1 | 5 | 6 | 5 & 6
12 | 100% | 33 | 25 | 30 | 50 | 12.a | 33 | 33 | 25 | 30 | 12.b | 33 | 33 | 30 | 50 | 2 | 7 | 8 | 7 & 8
13 | 100% | 105 | 75 | 100 | 150 | 13.a | 105 | 105 | 75 | 100 | 13.b | 105 | 105 | 100 | 150 | 3 | 9 | 10 | 9 & 10
14 | 100% | 10.2 | 6 | 10 | 15 | 14.a | 10.2 | 10.2 | 6 | 10 | 14.b | 10.2 | 10.2 | 10 | 15 | 4 | 11 | 12 | 11 & 12
15 | 100% | 49 | 10 | 45 | 100 | 15.a | 49 | 49 | 10 | 45 | 15.b | 49 | 49 | 45 | 100 | 5 | 13 | 14 | 13 & 14
16 | 100% | 40 | 20 | 35 | 75 | 16.a | 40 | 40 | 20 | 35 | 16.b | 40 | 40 | 35 | 75 | 6 | 15 | 16 | 15 & 16
17 | 100% | 11.8 | 8 | 12 | 15 | 17.a | 11.8 | 11.8 | 8 | 12 | 17.b | 11.8 | 11.8 | 12 | 15 | 7 | 17 | 18 | 17 & 18
21 | 100% | 13.2815 | 10.52 | 13.15 | 16.4375 | 21.a | 13.2815 | 13.2815 | 10.52 | 13.15 | 21.b | 13.2815 | 13.2815 | 13.15 | 16.4375 | 8 | 19 | 20 | 19 & 20
22 | 100% | 6.7065 | 3.945 | 6.575 | 9.8625 | 22.a | 6.7065 | 6.7065 | 3.945 | 6.575 | 22.b | 6.7065 | 6.7065 | 6.575 | 9.8625 | 9 | 21 | 22 | 21 & 22
23 | 100% | 1.3413 | 0.789 | 1.315 | 1.9725 | 23.a | 1.3413 | 1.3413 | 0.789 | 1.315 | 23.b | 1.3413 | 1.3413 | 1.315 | 1.9725 | 10 | 23 | 24 | 23 & 24
24 | 100% | 1.3413 | 0.789 | 1.315 | 1.9725 | 24.a | 1.3413 | 1.3413 | 0.789 | 1.315 | 24.b | 1.3413 | 1.3413 | 1.315 | 1.9725 | 11 | 25 | 26 | 25 & 26
31 | 100% | 18 | 10 | 15 | 35 | 31.a | 18 | 18 | 10 | 15 | 31.b | 18 | 18 | 15 | 35 | 12 | 27 | 28 | 27 & 28
32 | 100% | 2 | 1 | 2 | 3 | 32.a | 2 | 2 | 1 | 2 | 32.b | 2 | 2 | 2 | 3 | 13 | 29 | 30 | 29 & 30
33 | 100% | 4.8 | 1 | 5 | 8 | 33.a | 4.8 | 4.8 | 1 | 5 | 33.b | 4.8 | 4.8 | 5 | 8 | 14 | 31 | 32 | 31 & 32
34 | 100% | 2.2 | 1 | 2 | 4 | 34.a | 2.2 | 2.2 | 1 | 2 | 34.b | 2.2 | 2.2 | 2 | 4 | 15 | 33 | 34 | 33 & 34
35 | 100% | 2.1 | 1.5 | 2 | 3 | 35.a | 2.1 | 2.1 | 1.5 | 2 | 35.b | 2.1 | 2.1 | 2 | 3 | 16 | 35 | 36 | 35 & 36
36 | 100% | 1.08 | 0.9 | 1 | 1.5 | 36.a | 1.08 | 1.08 | 0.9 | 1 | 36.b | 1.08 | 1.08 | 1 | 1.5 | 17 | 37 | 38 | 37 & 38
37 | 100% | 1 | 0.5 | 1 | 1.5 | 37.a | 1 | 1 | 0.5 | 1 | 37.b | 1 | 1 | 1 | 1.5 | 18 | 39 | 40 | 39 & 40
38 | #REF! | 8.0797 | 4.7528 | 7.9213 | 11.8819 | 38.a | 8.0797 | 8.0797 | 4.7528 | 7.9213 | 38.b | 8.0797 | 8.0797 | 7.9213 | 11.8819 | 19 | 41 | 42 | 41 & 42
40 | #REF! | 46 | 20 | 45 | 75 | 40.a | 46 | 46 | 20 | 45 | 40.b | 46 | 46 | 45 | 75 | 20 | 43 | 44 | 43 & 44
97 | 100% | 2.53 | 0.32404 | 2.53 | 4.736 | 97.a | 2.53 | 2.53 | 0.32404 | 2.53 | 97.b | 2.53 | 2.53 | 2.53 | 4.736 | 21 | 45 | 46 | 45 & 46
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 22 | 47 | 48 | 47 & 48
#REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 23 | 49 | 50 | 49 & 50
|  | 48 | 45 | 46 | 47 | [11 empty] | Plot of Min, Mean and Max
General Uncertainties
RefNo. | Show? | Mean(OF) | Min(OF) | M.L.(OF) | Max(OF) |  | x1 | x2 | y1 | y2 |  | x2 | x3 | y2 | y3
A | 1 | 14 | -35 | 10 | 75 | A.a | 14 | 14 | -35 | 10 | A.b | 14 | 14 | 10 | 75 | 24 | 49 | 50 | 49 & 50
B | 1 | 5 | -25 | 0 | 50 | B.a | 5 | 5 | -25 | 0 | B.b | 5 | 5 | 0 | 50 | 25 | 51 | 52 | 51 & 52
C | 1 | 14 | -50 | 10 | 90 | C.a | 14 | 14 | -50 | 10 | C.b | 14 | 14 | 10 | 90 | 26 | 53 | 54 | 53 & 54
D | 1 | 8.5 | -5 | 10 | 17.5 | D.a | 8.5 | 8.5 | -5 | 10 | D.b | 8.5 | 8.5 | 10 | 17.5 | 27 | 55 | 56 | 55 & 56
E | 1 | -4 | -15 | -5 | 10 | E.a | -4 | -4 | -15 | -5 | E.b | -4 | -4 | -5 | 10 | 28 | 57 | 58 | 57 & 58
F | 1 | 16 | -25 | 10 | 75 | F.a | 16 | 16 | -25 | 10 | F.b | 16 | 16 | 10 | 75 | 29 | 59 | 60 | 59 & 60
G | 1 | 6 | -10 | 5 | 25 | G.a | 6 | 6 | -10 | 5 | G.b | 6 | 6 | 5 | 25 | 30 | 61 | 62 | 61 & 62
H | 1 | 19 | -25 | 15 | 75 | H.a | 19 | 19 | -25 | 15 | H.b | 19 | 19 | 15 | 75 | 31 | 63 | 64 | 63 & 64
I | 1 | 11 | -25 | 10 | 50 | I.a | 11 | 11 | -25 | 10 | I.b | 11 | 11 | 10 | 50 | 32 | 65 | 66 | 65 & 66
J | 1 | 17 | 5 | 15 | 35 | J.a | 17 | 17 | 5 | 15 | J.b | 17 | 17 | 15 | 35 | 33 | 67 | 68 | 67 & 68
K | 1 | 4 | -5 | 0 | 25 | K.a | 4 | 4 | -5 | 0 | K.b | 4 | 4 | 0 | 25
Z | 1 | 10 | -15 | 10 | 35 | Z.a | 10 | 10 | -15 | 10 | Z.b | 10 | 10 | 10 | 35
Mean values
|  | OF's | Posts | Factor
| Costs: | -4 | #REF! | 100% | dTF+(M) | 140.7% | #NAME? | The OF contribution.
| Income: | 124.5 | #REF! | 100% | dTF-(M) | 100% | #REF! | The OF contribution.
Diagram Text
General Uncertainties & Tasks
Mean= 0,0
General Uncertainties Tasks
| TF(Not actual)= 100,0% |  | Not actual
| TF(Consume)= 140,7% |  | Consume
General Uncertainties & Tasks
General Uncertainties TF(Consume)= 140,7% TF(Not actual)= 100,0%
General Uncertainties & Tasks General Uncertainties TF(Consume)= 140,7% TF(Not actual)= 100,0%
early-quality-assuring-construction-project_2024-11-19a.xlsx
Note on T2: Henrik K Søndergaard: In particular, when/if new elements are added.
Note on T3: Henrik K Søndergaard: Min, Max and ML of Posts

## CurveData (hidden)
[5 empty] | X2 | Y2 | X3 | Y3 | X5 | Y5 | X5 | Y5 | X6 | Y6 | X7 | Y7
|  | 1.0364 |  |  | 493.9603 | 0% | 0 | 50% | 0 | 85% | 556.789 | 0% | 0 | 95% | 593.6715 | 0%
| -3 |  | S-min |  | 493.9603 | 50% | 493.9603 | 50% | 556.789 | 85% | 556.789 | 85% | 593.6715 | 95% | 593.6715 | 95%
| 0.5 |  | dS | [5 empty] | Procentuel afvigelse
| 60.6201 |  | "GrandTotal_StDev" |  | "+NORMFORDELING(x;middelværdi;standardafv,kumulativ)
Search probability |  | 1.0364 | 85% |  | For no of standard deviation according to robust budget | [7 empty] | 95%
[9 empty] | 85% | 556.789
Search probability |  | 2.5 | 99.38% | [5 empty] | 50% | 493.9603
Search probability |  | -2.5 | 0.621% | [5 empty] | Usikkerhed= | 12.72%
Confidence interval |  | 5 | 98.76%
Seak Nul point
| *Stdev |  | X-Serie1 | No. | Y-Serie1 | X-Serie1 | No.
| -3 | -3 | 312.0999 | 1 | 0.135% | 312.0999 | 1
| -2.5 | -2.5 | 342.41 | 2 | 0.621% | 342.41 | 2
| -2 | -2 | 372.72 | 3 | 2.275% | 372.72 | 3
| -1.5 | -1.5 | 403.0301 | 4 | 6.681% | 403.0301 | 4
| -1 | -1 | 433.3402 | 5 | 15.87% | 433.3402 | 5
| -0.5 | -0.5 | 463.6502 | 6 | 30.85% | 463.6502 | 6
| 0 | 0 | 493.9603 | 7 | 50% | 493.9603 | 7
| 0.5 | 0.5 | 524.2704 | 8 | 69.15% | 524.2704 | 8
| 1 | 1 | 554.5804 | 9 | 84.13% | 554.5804 | 9
| 1.5 | 1.5 | 584.8905 | 10 | 93.32% | 584.8905 | 10
| 2 | 2 | 615.2005 | 11 | 97.72% | 615.2005 | 11
| 2.5 | 2.5 | 645.5106 | 12 | 99.38% | 645.5106 | 12
| 3 | 3 | 675.8207 | 13 | 99.87% | 675.8207 | 13

## PlotData
Request more information
for the full : Mail@compilot.dk

## Top10Esti
Request more information
for the full : Mail@compilot.dk